## Sheet1
Task | Time (Hours)
Reference/resource gathering | 10
Reference/resource analysis | 15
Reference/resource review | 5
System Requirements Specification Document | 10
Participant Gathering | 20
Work Breakdown Structure Document | 10
Develop questionnaire 1 | 15
Create user manual/install documentation | 10
Create user manual/feature explanation section | 10
Core functionality development | 50
Initial software testing | 20
Distribute project and documentation | 5
Software trial phase 1 | 20
Suggestions/improvements gathering | 10
Trial 1 feedback processing | 10
Software fixes | 10
Additional feature planning | 10
Additional features/fixes implementation | 25
Software testing | 20
User manual/documentation update | 5
Distribute updated project and documentation | 5
Develop questionnaire 2 | 10
Software trial phase 2 | 20
Suggestions/improvements gathering | 10
Trial 2 feedback processing | 10
Software Fixes | 10
Additional feature planning | 10
Additional features/fixes implementation | 25
Software testing | 20
User manual/documentation update | 5
Distribute updated project and documentation | 5
Software trial phase 3 | 20
Suggestions/improvements gathering | 10
Trial 3 feedback processing | 10
Data analysis/conclusions | 20
Total | 480